## Sheet1
Modules | Status | Tentative Days |  | Tentative Date | Resources
|  | Design | DB & Development
Workflow Master |  | 0.5 | 2 | 2019-12-18 | Divyanand T.
Project Master |  | 0.5 | 2 | 2019-12-18 | Aarti M.
Create Task |  | 0.5 | 5 | 2019-12-27 | Divyanand T.
View TaskList |  | 0.5 | 1 | 2020-01-03 | Aarti M.
Task Details - Partial View For Details |  | 0.5 | 1 | 2019-12-30 | Divyanand T.
Task Details - Partial View For Updating the task status |  | 0.5 | 4 | 2019-01-03 | Divyanand T.
Task Details - Partial View For Task Trail |  | 0.5 | 3 | 2019-01-09 | Aarti M.
Dashboard |  | 1 | 3 | 2019-01-09 | Divyanand T.
Reports |  | 0.5 | 6 | 2019-01-02 | & Divyanan T.

## Sheet2
Modules | Status | Tentative Days |  | Tentative Date | Resources
|  | Design | DB & Development
Email Workflow
- Creation of a new Db Context for Common Email Live | Done |  | 1 | 2020-02-18 | Aarti M.
- Integrating the entity call to Outbox SP | Done
- Mail Creation with JWT link for Task Creation/Members added Task Modification (Status Change/Comments/Files added) Reminders (To be discussed in future) | Done |  | 2 | 2020-02-20
Task Progress
- Adding Sub Tasks Weightage | Done |  | 3 | 2020-02-28 | Aarti M.
- Weightage calculation on completion of a task | Done |  | 3 | 2020-02-26 | Divyanand T.
- Display page for Project Progress | To Do |  | 1 | 2020-02-27 | Divyanand T.
- Display page for Task Progress | Done |  | 1 | 2020-02-28 | Divyanand T.
Start - Stop Task
- Coding for Start with Audit | Done |  | 2 | 2020-02-18 | Aarti M.
- Coding for Stop with Audit | Done |  | 2 | 2020-02-20 | Aarti M.
Rights Implementation
- Admin Rights creation for Dashboard View | TO DO |  | 2 | 2020-02-26 | Utsav P.
Dashboard Creation
- Creation of Visual Graphical Report for As On Time Usage | Done | 2 | 2 | 2020-02-25 | Utsav P.
- Creation of Visual Graphical Report for Project Wise/Resource Wise Usage | WIP |  | 3 | 2020-02-28 | Utsav P.
Reports
- Task wise Start Stop Report |  |  | 2 | 2020-02-28 | Aarti M.
Release on UAT |  |  |  | 2020-02-28
Testing and QC Check |  |  | 5 | 2020-03-05 | Pankaj V. Rathin D.
Miscellaneous tasks
- Task Status "Complete" Logic | Done |  | 5 | 2020-03-05 | Aarti M.
- UI Enhancements |  |  |  |  | Aarti M.
- Bug Resolving |  |  |  |  | Divynanad T.
Go LIVE |  |  |  | 2020-03-06

## Phase 1.5
Modules | Status | Tentative Days |  | Tentative Date | Resources
|  | Design | DB & Development
Total of the weightage to be shown wherever we are adding the weightage in the list. Task Reference Column. |  |  | 1 | 2020-04-03 | Aarti | sum to calculate weightage.
Comments List to be added along with the files in the same list below the Comments box |  |  | 2 | 2020-04-08 | Aarti | comment and file section separtely
API creation / updation as needed by the mobile environment |  |  | 1 | 2020-04-03 | Divyanand
Report for employees to see their own Start Stop in the day. |  |  | 1 | 2020-04-09 | Aarti | My Task activity report. New report.
Graphical Report for Admin dashboard |  |  | 2 | 2020-04-08 | Divyanand
Bugs resolution of Phase 1 |  | As it comes |  |  | Divyanand

## Phase 2
Modules | Status | Tentative Days |  | Tentative Date | Resources
|  | Design | DB & Development
Task cannot be marked as completed till all the employees 'STOP' working. |  |  | 2 | 2020-04-06 | Divyanand
Change the 'Closed' Status name to 'Invalidate' and disable the task. |  |  | 2 | 2020-04-08 | Divyanand
Add File Links in Trail History and Comments History |  |  | 2 | 2020-04-12 | Divyanand
Tree View from Module Level to Leaf node |  |  | 3 | 2020-04-15 | Divyanand
Search for Project and Module in all the listing page |  |  | 1 | 2020-04-18 | Divyanand
Time difference for duration in all the report pages |  |  | 1 | 2020-04-19 | Divyanand
Testing |  |  | 1 | 2020-04-20 | Rathin